## Sheet1
HSC SEN Major Project - Dispatch Asset Management | WEEK 1 | [5 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
Key: Proposed
Key: Actual | time axis 2025-04-28 to 2025-07-02
Tasks | time axis 2025-04-28 to 2025-07-02
Identifying and Defining
Define + Analyse: Problem Requirements | bar: 2025-04-28 to 2025-05-17
— demonstrating need(s) or opportunities | bar: 2025-04-28 to 2025-04-30
— assessing scheduling and financial feasibility | bar: 2025-04-28 to 2025-04-30
— generating requirements: functionality and performance | bar: 2025-04-28 to 2025-04-30
— defining boundaries/limitations | bar: 2025-04-30 to 2025-05-10
Idea/Solution Development - Documentation of:
— brainstorming, mind mapping and storyboards | bar: 2025-04-30 to 2025-05-09
— algorithm design | bar: 2025-05-04 to 2025-05-24
— code development (screenshots of) | bar: 2025-05-18 to 2025-06-22
— testing and debugging (screenshots of) | bar: 2025-05-18 to 2025-06-22
— installation and maintenance | bar: 2025-06-15 to 2025-06-29
Research and Planning
Project management: Gantt Chart | bar: 2025-05-05 to 2025-07-01
QA: creating a Criteria of Quality | bar: 2025-05-10 to 2025-05-19
QA: Protocol/Legislation Compliance | bar: 2025-06-14 to 2025-06-22
Modeling Tools; DFDs, Data Flow, Structure Chart | bar: 2025-05-07 to 2025-05-21
Producing and Implementing
Create: Back-end for program, handling of database | bar: 2025-05-18 to 2025-06-22
Create: Front-end UI, forms, buttons, icons | bar: 2025-05-18 to 2025-06-22
Develop: Front-end interface accessibility (CSS) | bar: 2025-06-01 to 2025-06-22
Develop: Latter should-do/could-do features | bar: 2025-06-07 to 2025-06-22
Testing and Evaluating
QA: Testing and Debugging process | bar: 2025-05-18 to 2025-06-22
Evaluate and test whole product against criteria | bar: 2025-06-21 to 2025-06-29
Develop: optimisation (front-end UI and back-end) | bar: 2025-06-07 to 2025-06-29